## Sheet1
Multi Sector Action Plan for Nutrition 2018
S.No | programme | Process of conducting | Detailed discription of expected expenditure | Responsibility
1 | conduct a practical session on prepare a nutrious meal and aware mothers on best child care practices(8 programmes) | Period - September to December Venue - Community Halls and PHM offices of selected villages. Discussing Sections - * Importance of Nutrious meals *Importance of food diversification *Importance of locally available foods * Practical session of How to make a nutritional meal using locally available foods Resource persons- Medical Officer of Health (Dehiattakandiya)/ Public Health Nursing Sister/ Supervising Public Health Midwife Expected participation - 40 mothers | Per one programme - matierial cost :- 5000.00 Resource person fees - Stationary costs - for 08 Programmes Rs.5000.00X8 = 40,000.00 Total cost =40,000 | Divsonal Secaratriat (In collobration with MOH office)
3 | Conduct a home gardenning competition among nutrition at risk families (Selected 100 families) | Period - August to December Process of Conducting 1. Select the 2 houses per village through the DO/GS/SDO/PHM/ARPA 2. Conduct training programme for those who selected of the nutritionally at-risk households on *Home gardenning techniques * Proper maintains of home gardens and monitoring 3. Select the best home garden and giving prizes for them Resource person - Agriculture Inspector | Resource person fees - 500x3 = 1500 Refreshments- 50x100=5000 Stationary Costs - 30x100 =3000 Other cost - Gifts 1st palce :- 7500.00 2nd place :- 5000.00 3rd place :- 3000.00 =15,500 Total cost =26,000 | DS/ ADP/AI
4 | conduct a training programme for low income, nutrition at risk families on self employment opportunities (50) |  | resource person :- 1500.00 refreshments :- 50x50 = 2500.000 = 4000.00
5 | conduct a awareness programme on nutrition for early married couples (50 couples/* 100 persons) | Time - 15th of October Discussing sections *Importance of nutritions of pre-pregnent womens *Pregnancy and nutrition Resource persons - Medical Officer of Health (Dehiattakandiya) | refreshment:- 50x100 = 5000 Resource person fees 900x2=1800 Total cost =6800 | DS/ MOH/ADP
6 | conduct a awareness programme on nutrition for grade 10 for 500 girls students | Time - 15th of September Discussing sections *Importance of nutritions teenage girls *How to avoid pregnancy at teenage *Pregnancy and nutrition Resource persons - Medical Officer of Health (Dehiattakandiya) | Refreshment:- 50x200 = 10000 Resource person fees:- 900x2 =1800 Stationary cost :- 30x200 = 6000 Total cost =17,800
7 | conduct a yearend appriciation programme for officers, mothers support groups and social workers who contribute to success the programme | Reduction in number of low weight children | Best PHM (certificate) Best DO (certificate) :- 500.00 Best mother support group (10) gifts :- 5000.00 certificates :-500.00 Best social workers gift :- 1000.00 =7000.00

## Sheet2
Multi Sector Action Plan for Nutrition 2018 -Dehiattakandiya.
S.No | Programme | Process of conducting |  | Detailed discription of expected expenditure | Responsibility
1 | Conduct a practical session on prepare a nutrious meal and aware mothers on best child care practices(6 programmes) | Period - September to December |  | Per one programme - | DS/ MOH/ADP
|  |  | Venue - Community Halls and PHM offices of selected villages. | matierial cost :- 5000.00
|  | Discussing Sections - |  | Resource person fees -
|  |  | * Importance of Nutrious meals | Stationary costs -
|  |  | *Importance of food diversification | for 06 Programmes
|  |  | * Practical session of How to make a nutritional meal using locally available foods | Rs.4000.00X6 = 24,000.00
|  |  | Resource persons- Medical Officer of Health (Dehiattakandiya)/ Public Health Nursing Sister/ Supervising Public Health Midwife | Total cost =24,000
Expected participation - 40 mothers
2 | Conduct a home gardening competition among nutritionally at-risk families (Selected 10 PHM areas) | Period - August to December |  | Resource person fees - 500x3 = 1500.00 | DS/ ADP/AI
|  | Process of Conducting |  | Refreshments- 50x100=5000.00
|  |  | 1. Select 10 houses per PHM areas through DO /GN / PHM /ARPA | Stationary Costs - 30x100 =3000.00
|  |  | 2. Conduct training programme for those who selected of nutritionally at-risk households on | Other cost -
|  |  | *Home gardening techniques | Gifts
|  |  | * Proper maintains of home gardens and monitoring | 1st palce :- 5000.00
|  |  | 3. Select best home gardens and giving prizes for them | 2nd place :- 3000.00
3rd place :- 2000.00
4th- 10th places:- 1000 x 7 =7000.00
|  |  | Resource person - Agriculture Inspector | travalling claims:-10x300=3000.00(for 10 officers)
|  |  | Expected participation - 100 nutritionally at-risk families | Total cost =29,500
3 | Conduct a training programme for low income, nutrition at risk families on self employment opportunities (50) | Date - 30th of september |  | resource person fees:- 3x500 =1500 | DS/ADP
|  | Venue - Conference hall of Divisional seceratriat |  | refreshments :- 50x50 = 2500
|  | Discussing Sections - |  | Stationary cost :- 30x50=1500
|  |  | Introduce opportunities of self employment | Total Cost =5500
Expected participation - 50
Resource Person : Development Officer.
4 | Conduct a awareness programme on nutrition for early married couples (50 couples/* 100 persons) | Date - 15th of October |  | refreshment:- 50x100 = 5000 | DS/ MOH/ADP
|  | Discussing sections |  | Resource person fees 900x2=1800
|  |  | *Importance of nutritions of pre-pregnent womens | stationary cost 50x50= 2500
*Pregnancy and nutrition
Resource persons -
|  |  | Medical Officer of Health (Dehiattakandiya) | Total cost =9300
Expected participation- 100 persons
5 | Conduct a awareness programme on nutrition for 100 grade 10 girl students(selected 3 schools) | Time - 15th of September |  | refreshment:- 50x100 = 5000 | DS/ MOH/ADP
|  | Discussing sections |  | Resource person fees 900x2=1800
|  |  | *Importance of nutritions for teenage girls | Stationary cost 100x25= 2500
*How to avoid pregnancy at teenage
|  |  | *Pregnancy and nutrition | Total cost =9300
Resource persons - Medical Officer of Health (Dehiattakandiya)
Expected participation - 100
6 | Exihibition on Nutrition and food habits | Date 30th of Octomer |  | Stationary cost- 5000.00 | DS/ MOH/ADP
Discussing Sections
|  |  | *Importance of nutritions for teenage, pregnancy and childhood. | matierial cost :- 10000.00
|  |  | * Preparation of a balanced diet and its importance. | Total cost- 15000.00
*Importance of food diversification.
*Introduce good food habits .
*How to avoid bad food habits, false belifes, myths and customs.
Process of conducting
*Displaying banners and posters about Nutrition, Food habits ect..
*Dislaying video clips on above discussing Sections
*Displaying samples of balanced food diet and Nutrious foods ect…
7 | Conduct an yearend appriciation programme for officers, mothers support groups and social workers who contribute to success the programme | Selection criteria |  |  | DS/ MOH/ADP
|  |  | * Percentage of deduction nutritionally at-risk children | Stationary cost 400
|  |  | * Number of succesfull home gardens | gifts
|  |  | Ect…….. | 1st price 4000
2nd price 3000
3rd place 1500
|  |  | *Best PHM (certificate) | prepare and publish a report(5 copies) 800x5 = 4000
|  |  | *Best DO (certificate) | Total cost = 12,900
*Best GN (certificate)
*Best mother support group (gifts and certificate)
*prepare and publish a report of annual programmes under the multi Sector Action Plan for Nutrition 2018 for Dehiattakandiya Divisional Secretariat Area
GRAND TOTAL = 105,500